## Sheet1
All DOCUMENTS READER VIEW DOCS
Identified By : Reshma Krishna |  |  |  | Verified By : Reshma Krishna
Environment Details : Andriod 10 |  |  |  | Date : 31/01/2023
BUG ID | EXPECTED RESULT | BUG DISCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | SCREENSHOT | STATUS
DEF_ADR_01 | Home page should be loaded after splash screen | Splash screen does not automatically redirect to home page | 1. Navigate to app icon 2. Open the app | Enhancement |  |  | New
DEF_ADR_02 | App orientation shoud change in landscape mode and portrait mode | App Orientation does not change in landscape mode | 1. Navigate to app icon 2. Open the app 3. Click the 'Get starterd' button 4. Change orientation to landscape and portrait mode | Minor |  |  | New
DEF_ADR_03 | Option to view all files in landscape and portrait mode should be present | Files cannot be viewed in landscape mode | 1. Open the Application 2. Click the 'All files' button or any category of files 3. Open files in landscape and portrait mode | Minor |  |  | New
DEF_ADR_04 | Formatting of the Docx file should not change when opened | Docx file Fomat is different from the orginally applied format | 1. Open the app 2. Click the Docx file' button 3. Click a Docx file | Minor |  | https://drive.google.com/file/d/1G47RIR0svMs4b0LTuBKvRKGUnS37HGPP/view?usp=drivesdk | New
DEF_ADR_05 | Pages and fonts should change from light to dark in dark mode and vise versa in light mode | Contents of the page are all blended white in dark mode | 1. Open the Application 2. Click the 'DOCX Files' button 3. Open a DOCX file in dark mode | Major |  | https://drive.google.com/file/d/1FzYUQjreGJfnZFnBCCXg0a9YoZT01B_S/view?usp=drivesdk | New
DEF_ADR_06 | Should be able to go to previous page after clicking back button from docx viewing page | Shows a black screen and only restores to normal state when app is restarted. | 1. Open the application 2. Click on 'DOCX Files' button 3. Open a DOCX file 4. Locate and click back button | Blocker |  |  | New
DEF_ADR_07 | Formatting of the PDF files should not change when opened | Contents appear to be stretched vertically | 1. Open the application 2. Click 'PDF Files' button 3. Open a PDF file | Trivial |  | https://drive.google.com/file/d/1G3qL7MUWfr4DPV5ItlHkfy8iBnsPUj7d/view?usp=drivesdk | New